## Slide 1
FLIGHT HACK 2.0
IDEA SUBMISSION DECK
Program Management Track
Idea Title: Predictive Turnaround Optimization (PTO)
Submitted by: Program Management Team
Date: August 2026
FLIGHT HACK 2.0 | PROGRAM MANAGEMENT TRACK
1

## Slide 2
THE PROBLEM
Turnaround Delays Are Eroding
On-Time Performance
Ground turnaround is the single largest source of controllable schedule variance. Manual coordination across fueling, cleaning, catering, and boarding crews creates blind spots that cascade into network-wide delays.
38 min
Avg. turnaround
overrun (peak hrs)
₹210 Cr
Estimated annual
cost of delay
62%
Delays traced to
coordination gaps
AIRCRAFT
Fueling
Cleaning
Catering
Baggage
Boarding
Maint.
Uncoordinated ground service touchpoints
FLIGHT HACK 2.0 | PROGRAM MANAGEMENT TRACK
2

## Slide 3
THE IDEA
A Predictive, Single-Pane
Turnaround Control Tower
PTO fuses live flight, crew, and ground-service data into one predictive dashboard — flagging turnaround risk 20 minutes before it happens and auto-notifying the right ground team.
1
Predict
ML model forecasts turnaround risk from live inbound data.
2
Unify
One dashboard replaces five siloed ground-ops tools.
3
Alert
Auto-notifies the right crew the moment a delay risk appears.
4
Learn
Post-flight analytics tune the model turn over turn.
FLIGHT HACK 2.0 | PROGRAM MANAGEMENT TRACK
3

## Slide 4
PM APPROACH
Program Governance Model
A phased, hybrid-agile delivery model with a dedicated steering layer to manage cross-functional dependencies across IT, Ground Ops, and Safety.
Steering Committee
VP Ops, VP IT, Program Sponsor — monthly gate reviews & risk escalation
Program Management Office
Cross-track planning, RAID log, budget & benefits tracking
Delivery Squads
Data Eng · ML · Dashboard UX · Ground Ops Integration — 2-week sprints
DELIVERY CADENCE
1
Discovery & data audit
2
MVP dashboard (1 hub)
3
Predictive model pilot
4
Network-wide rollout
5
Hypercare & optimize
FLIGHT HACK 2.0 | PROGRAM MANAGEMENT TRACK
4

## Slide 5
SCOPE & OBJECTIVES
What's In, What's Out
IN SCOPE
Predictive risk model for 4 metro hub airports
Unified ground-ops dashboard (web + tablet)
Automated crew alerting via SMS / app push
Integration with existing flight-ops data feed
Post-turnaround analytics & benefits reporting
OUT OF SCOPE (Phase 1)
Regional / turboprop stations
Full crew-scheduling system replacement
Cargo & belly-freight turnaround workflows
Third-party ground handler contract changes
Primary Objective: Cut average turnaround overrun by 40% at pilot hubs within 2 quarters of go-live.
FLIGHT HACK 2.0 | PROGRAM MANAGEMENT TRACK
5

## Slide 6
ROADMAP
Implementation Timeline
12-month phased rollout across four milestones
M1–M2
Discovery &
Data Audit
M3–M5
MVP Dashboard
Pilot Hub
M6–M8
Predictive Model
Calibration
M9–M12
Network Rollout
& Hypercare
Chart: Cumulative Overrun Reduction Target
| M2 | M5 | M8 | M12
Target Overrun Reduction (%) | 5 | 15 | 28 | 40
FLIGHT HACK 2.0 | PROGRAM MANAGEMENT TRACK
6

## Slide 7
RESOURCE PLAN
Team & Budget Envelope
ROLE
HEADCOUNT
ALLOCATION
Program Manager
1
100%
Data Engineers
2
100%
ML Engineer
1
100%
Product / UX Designer
1
75%
Ground Ops SME
1
50%
QA / Release Engineer
1
50%
Chart: Budget Allocation (%)
| Engineering | Data & ML | Ground Ops Integration | Contingency
Budget Allocation | 42 | 28 | 18 | 12
Total Program Budget ₹4.8 Cr over 12 months
FLIGHT HACK 2.0 | PROGRAM MANAGEMENT TRACK
7

## Slide 8
RISK MANAGEMENT
Top Program Risks & Mitigations
High
Ground-ops data feeds are inconsistent across hubs
Mitigation: Run a 2-week data-quality audit before MVP build begins
Med
Frontline crew adoption resistance to a new app
Mitigation: Co-design UI with ground crews; phased hub-by-hub rollout
Med
Model false-positive alerts erode trust early on
Mitigation: Human-in-the-loop review during first 60 days of pilot
High
Integration delay with legacy flight-ops system
Mitigation: Secure IT integration slot in sprint 1; API contract signed upfront
FLIGHT HACK 2.0 | PROGRAM MANAGEMENT TRACK
8

## Slide 9
SUCCESS METRICS
How We'll Measure Success
40%
Reduction in avg.
turnaround overrun
₹3.1 Cr
Projected annual
delay-cost savings
90%
Crew alert
acknowledgement rate
<15 min
Model prediction
lead time
PILOT-PHASE TRACKING CADENCE
Weekly
Ops dashboard review
Program Manager + Ground Ops Lead
Monthly
Steering committee readout
PMO + Sponsors
Quarterly
Benefits realization audit
Finance + PMO
FLIGHT HACK 2.0 | PROGRAM MANAGEMENT TRACK
9

## Slide 10
THE ASK
What We Need to Move Forward
1
Sponsorship
Executive sponsor from Ground Ops to co-chair steering committee
2
Seed Budget
₹40L discovery-phase budget to fund data audit + MVP build
3
Pilot Hub Access
Approval to pilot at one metro hub for 90 days starting Q4
4
Data Access
Read access to live flight-ops and ground-crew scheduling feeds
LET'S TALK
Ready to pilot this at
your hub next quarter.
PROGRAM LEAD
Program Management Team
TRACK
Program Management
SUBMISSION
Flight Hack 2.0
THANK YOU
FLIGHT HACK 2.0 | PROGRAM MANAGEMENT TRACK
10